CHAMCHAM

Influencer Marketplace Platform

Product Feature Document & Sprint Plan

Version 1.0  |  May 2026

8 Sprints  ·  16 Weeks  ·  Pakistan Market

# 1. Product Overview

ChamCham is a two-sided influencer marketplace connecting brands with social media creators (TikTok, Instagram, YouTube) for authentic, performance-driven marketing collaborations. The platform is purpose-built for the Pakistan market with plans to scale across emerging markets.

## Platform Goals

- Enable brands to discover, evaluate, and hire the right creator quickly

- Allow creators to showcase their audience, packages, and monetize their influence

- Support flexible deal structures: cash payments and in-kind/barter collaborations

- Provide admin oversight for quality control, trust, and dispute resolution

- Become the leading creator-brand marketplace in Pakistan

## User Roles

- Brand — discovers creators, purchases packages, manages campaigns

- Creator — builds profile, defines packages, fulfils orders

- Admin — oversees platform quality, verifications, disputes

# 2. Feature Breakdown

The following sections detail each major feature area of ChamCham, with description, user benefit, and implementation priority.

## 2.1  Authentication & Onboarding

Users register as either a Brand or Creator. Each role has a dedicated onboarding flow that captures role-specific information needed to use the platform effectively.

| Feature | Description | Priority |
| --- | --- | --- |
| Role Selection | During sign-up users choose Brand or Creator, unlocking role-specific dashboards and features. | Critical |
| Email / Social Sign-up | Standard email registration with optional Google/social OAuth for faster onboarding. | Critical |
| Brand Onboarding | Captures brand name, industry, website, campaign goals, and billing info. | Critical |
| Creator Onboarding | Captures creator bio, niche categories, social handles, follower counts, and portfolio. | Critical |
| Profile Verification | Admin-triggered identity and social account verification badge for creators. | High |

## 2.2  Creator Profile

Each creator has a public-facing profile page that brands can visit to evaluate fit. The profile is the creator's storefront on ChamCham.

| Feature | Description | Priority |
| --- | --- | --- |
| Profile Header | Displays creator name, location, avatar, cover image, response time, completion rate, and repeat clients. | Critical |
| Bio & Niche Tags | Short bio paragraph with category tags (Food, Fashion, Tech, Lifestyle, etc.). | Critical |
| Platform Stats | Aggregate follower count, average engagement rate, rating, and completed orders. | Critical |
| Social Links | Per-platform breakdown: Instagram, TikTok, YouTube — with follower count and engagement per platform. | Critical |
| Packages Section | Featured, trending, barter-friendly, and best-performing package categories. | Critical |
| Portfolio | Gallery of past work samples, campaign results, and brand collaborations. | High |
| Reviews & Ratings | Brand reviews with star ratings visible on the public profile. | High |
| Verification Badge | Verified, Elite, or Emerging status badge displayed on cards and profile. | Medium |

## 2.3  Creator Discovery & Search

Brands need powerful tools to find the right creator. The Explore page is the primary discovery surface and serves as the marketplace homepage for brands.

| Feature | Description | Priority |
| --- | --- | --- |
| Explore / Browse Page | Full creator listing page with cards showing key stats, badges, and a Quick Deal CTA. | Critical |
| Category Filter | Filter by niche: Food, Fashion, Tech, Beauty, Fitness, Travel, Gaming, Lifestyle. | Critical |
| Advanced Filters | Filter by follower range, engagement rate, price range, location, response time, barter availability. | High |
| Search | Keyword search across creator names, bios, and tags. | High |
| Platform Ambassadors | A separate curated section for platform-verified premium creators with 100K+ followers and 5%+ engagement. | High |
| Trending / Featured | Homepage sections: Trending Creators, Rising Stars, Verified Creators. | Medium |
| Creator Badges | Visual badge system: Verified (⭐), Elite (👑), Emerging (🚀) — shown on cards. | Medium |

## 2.4  Collaboration Packages

Creators define structured service packages that brands can directly purchase. Packages remove ambiguity from negotiations and accelerate deal closure.

| Feature | Description | Priority |
| --- | --- | --- |
| Package Creation | Creators build packages with title, deliverables list, delivery time, and price. | Critical |
| Cash Packages | Standard paid packages with a fixed SAR/PKR price and delivery timeline. | Critical |
| Barter Packages | In-kind packages where the brand provides meals, products, or services instead of cash. Creator defines the expected barter value and conditions. | Critical |
| Hybrid Packages | Combination of partial cash + partial in-kind compensation. | High |
| Subscription Packages | Recurring monthly collaboration packages for long-term brand ambassador arrangements. | High |
| Package Categories | Featured, Trending, Barter-Friendly, Best Performing groupings on creator profiles. | Medium |
| Quick Deal | One-click offer initiation from a creator card, sending a package offer directly without browsing the full profile. | High |

## 2.5  Messaging & Communication

Direct messaging enables brands and creators to discuss requirements, negotiate terms, and coordinate deliverables without leaving the platform.

| Feature | Description | Priority |
| --- | --- | --- |
| Direct Messaging | Real-time chat between a brand and a creator, initiated from the creator profile or Quick Deal flow. | Critical |
| Message Notifications | In-app and email notifications for new messages. | High |
| File / Media Sharing | Ability to share briefs, content drafts, and images within the chat. | High |
| Response Time Indicator | Creator profile displays average response time (e.g., Within 2 hours) to set expectations. | Medium |

## 2.6  Order Management

Once a package is purchased or a Quick Deal offer is accepted, an order is created. Both parties can track progress, submit deliverables, and release payment.

| Feature | Description | Priority |
| --- | --- | --- |
| Order Creation | Automatically generated when a brand purchases a package or accepts a Quick Deal. | Critical |
| Order Status Tracking | Status pipeline: Pending → In Progress → Deliverable Submitted → Approved → Completed. | Critical |
| Deliverable Submission | Creators upload content links or files as deliverables within the order. | Critical |
| Brand Review & Approval | Brands review submitted content and either approve or request revisions. | Critical |
| Brand Orders Dashboard | List view of all active and past orders for a brand, with status filters. | High |
| Creator Orders Dashboard | Creator view of all incoming orders, earnings, and delivery deadlines. | High |
| Revision Requests | Structured revision flow with comments and round limits. | Medium |

## 2.7  Payments & Billing

ChamCham handles secure payment processing for cash deals, while barter deals are coordinated through the platform but fulfilled offline.

| Feature | Description | Priority |
| --- | --- | --- |
| Escrow / Secure Payments | Brand funds are held in escrow and released to creator upon order approval. | Critical |
| Barter Deal Coordination | Platform facilitates barter deal terms and confirmations; fulfillment is offline. | Critical |
| Payment Release | Automatic or manual payment release upon brand approval of deliverables. | Critical |
| Creator Earnings Dashboard | Summary of total earned, pending, and withdrawn amounts. | High |
| Withdrawal / Payout | Creator requests withdrawal to bank account or mobile wallet. | High |
| Platform Fee | ChamCham deducts a configurable service fee percentage per transaction. | High |
| Brand Subscription Plans | Starter (free), Growth (monthly), Enterprise (custom) tiers with feature limits. | Medium |

## 2.8  Ambassador Program

A curated tier of top creators who are vetted and managed by the ChamCham platform. Ambassadors get guaranteed monthly income and dedicated account support.

| Feature | Description | Priority |
| --- | --- | --- |
| Ambassador Application | Creators apply through a dedicated portal; reviewed and approved by admin. | High |
| Ambassador Profile Badge | Special Ambassador badge and priority placement in search/listings. | High |
| Dedicated Account Manager | Each ambassador is assigned a platform account manager. | Medium |
| Monthly Guaranteed Deals | Platform negotiates minimum monthly deal volumes for ambassadors. | Medium |
| Performance Bonuses | Incentive structure for exceeding campaign performance benchmarks. | Low |

## 2.9  Admin Panel

The admin panel gives the ChamCham operations team oversight and control over the entire marketplace.

| Feature | Description | Priority |
| --- | --- | --- |
| Creator Verification | Admin reviews and approves creator verification requests and badge upgrades. | Critical |
| User Management | View, suspend, or ban brand and creator accounts. | Critical |
| Order Oversight | Admin can view all orders, intervene in disputes, and process refunds. | Critical |
| Content Moderation | Flag and review creator profiles and campaign content for policy violations. | High |
| Analytics Dashboard | Platform-wide metrics: GMV, active users, orders, categories, growth trends. | High |
| Ambassador Management | Approve ambassador applications, assign managers, track performance. | High |
| Pricing / Fee Management | Configure platform fee percentages and subscription plan features. | Medium |

# 3. Sprint Plan  (8 Sprints × 2 Weeks = 16 Weeks)

Sprints are ordered by dependency and business impact. Core marketplace functionality ships first; advanced features and monetization layer build on top.

## Sprint 1  |  Weeks 1–2  —  Foundation & Auth

Goal: Establish project scaffold, design system, CI/CD pipeline, and user authentication for both Brand and Creator roles.

| # | User Story | Feature Area | Priority |
| --- | --- | --- | --- |
| 1.1 | As a user I can sign up as Brand or Creator and receive a role-based dashboard | Auth & Onboarding | Critical |
| 1.2 | As a user I can log in with email and password with secure session management | Auth & Onboarding | Critical |
| 1.3 | As a user I can reset my password via email link | Auth & Onboarding | Critical |
| 1.4 | Set up shared design system: color tokens, typography, component library | Design System | Critical |
| 1.5 | Configure CI/CD pipeline, staging environment, and database schema (v1) | Infrastructure | Critical |

## Sprint 2  |  Weeks 3–4  —  Creator Profile

Goal: Build the full creator profile page — the core discovery surface that brands evaluate before initiating a deal.

| # | User Story | Feature Area | Priority |
| --- | --- | --- | --- |
| 2.1 | As a creator I can complete my onboarding profile with bio, niche tags, location, and social handles | Creator Profile | Critical |
| 2.2 | As a creator I can upload a profile photo and cover image | Creator Profile | Critical |
| 2.3 | As a brand I can view a creator's public profile with stats, bio, and platform breakdown | Creator Profile | Critical |
| 2.4 | As a creator I can add portfolio items (images, video links, past campaigns) | Creator Profile | High |
| 2.5 | Creator profile displays response time, completion rate, and repeat client count | Creator Profile | High |

## Sprint 3  |  Weeks 5–6  —  Creator Discovery & Explore

Goal: Launch the Explore page with browsing, filtering, and category-based discovery so brands can find relevant creators.

| # | User Story | Feature Area | Priority |
| --- | --- | --- | --- |
| 3.1 | As a brand I can browse all creators on the Explore page with creator cards | Discovery | Critical |
| 3.2 | As a brand I can filter creators by niche category (Food, Fashion, Tech, etc.) | Discovery | Critical |
| 3.3 | As a brand I can search creators by keyword (name, bio, tags) | Discovery | High |
| 3.4 | As a brand I can apply advanced filters: follower range, engagement, price, barter availability | Discovery | High |
| 3.5 | Creator cards display badge, rating, follower count, engagement rate, and starting price | Discovery | High |
| 3.6 | Homepage shows Trending, Rising Stars, and Verified Creators sections | Discovery | Medium |

## Sprint 4  |  Weeks 7–8  —  Packages & Quick Deal

Goal: Enable creators to define collaboration packages and brands to purchase or initiate Quick Deal offers.

| # | User Story | Feature Area | Priority |
| --- | --- | --- | --- |
| 4.1 | As a creator I can create cash packages with title, deliverables, delivery time, and price | Packages | Critical |
| 4.2 | As a creator I can create barter packages defining the expected in-kind value and conditions | Packages | Critical |
| 4.3 | As a brand I can view categorized packages on a creator profile and click Order Now | Packages | Critical |
| 4.4 | As a brand I can initiate a Quick Deal from a creator card without visiting the full profile | Packages | High |
| 4.5 | As a creator I can create subscription/recurring packages for long-term brand deals | Packages | High |
| 4.6 | Package sections display correctly: Featured, Trending, Barter-Friendly, Best Performing | Packages | Medium |

## Sprint 5  |  Weeks 9–10  —  Messaging

Goal: Real-time messaging between brands and creators, with notifications to keep both parties informed.

| # | User Story | Feature Area | Priority |
| --- | --- | --- | --- |
| 5.1 | As a brand I can send a message to a creator from their profile or Quick Deal flow | Messaging | Critical |
| 5.2 | As a creator/brand I can view all conversations in a Messages inbox | Messaging | Critical |
| 5.3 | As a user I receive in-app and email notifications for new messages | Messaging | High |
| 5.4 | As a user I can share files and images in a conversation (briefs, draft content) | Messaging | High |
| 5.5 | Message thread is linked to the relevant order once a deal is initiated | Messaging | Medium |

## Sprint 6  |  Weeks 11–12  —  Orders & Campaign Tracking

Goal: Full order lifecycle management from creation through to delivery approval and completion.

| # | User Story | Feature Area | Priority |
| --- | --- | --- | --- |
| 6.1 | An order is automatically created when a brand purchases a package or Quick Deal is accepted | Orders | Critical |
| 6.2 | As a creator I can view active orders, submit deliverables (links/files), and mark complete | Orders | Critical |
| 6.3 | As a brand I can view all my campaigns in Orders dashboard with status filters | Orders | Critical |
| 6.4 | As a brand I can approve deliverables or request a revision with comments | Orders | Critical |
| 6.5 | Order status pipeline: Pending → In Progress → Submitted → Approved → Completed | Orders | Critical |
| 6.6 | As a user I receive order status change notifications | Orders | High |
| 6.7 | Barter order flow captures in-kind delivery confirmation from both parties | Orders | High |

## Sprint 7  |  Weeks 13–14  —  Payments, Reviews & Admin Panel

Goal: Secure payment handling, creator payouts, brand and creator review system, and core admin tools.

| # | User Story | Feature Area | Priority |
| --- | --- | --- | --- |
| 7.1 | As a brand I can pay for a package via escrow; funds are held until order completion | Payments | Critical |
| 7.2 | As a creator I can withdraw earnings to bank/mobile wallet from earnings dashboard | Payments | Critical |
| 7.3 | Platform automatically deducts a service fee and disburses creator payment on approval | Payments | Critical |
| 7.4 | As a brand I can leave a star rating and review after order completion | Reviews | High |
| 7.5 | Reviews are displayed on the creator public profile | Reviews | High |
| 7.6 | As an admin I can verify creators and assign badge levels (Verified, Elite, Emerging) | Admin | Critical |
| 7.7 | As an admin I can view, suspend, or ban user accounts | Admin | Critical |
| 7.8 | As an admin I can access all active orders and intervene in disputes | Admin | High |

## Sprint 8  |  Weeks 15–16  —  Ambassador Program, Pricing Tiers & Polish

Goal: Launch the Ambassador tier, brand subscription plans, analytics, and complete platform polish before go-to-market.

| # | User Story | Feature Area | Priority |
| --- | --- | --- | --- |
| 8.1 | As a creator I can apply to the Ambassador program via the creator portal | Ambassador | High |
| 8.2 | Ambassador creators are listed in a dedicated section with exclusive badge and benefits | Ambassador | High |
| 8.3 | As a brand I can subscribe to Starter (free), Growth, or Enterprise plans | Pricing | High |
| 8.4 | Plan limits enforced: Starter = 5 offers/month; Growth = unlimited + insights | Pricing | High |
| 8.5 | Admin analytics dashboard: GMV, active users, orders volume, top categories | Admin Analytics | High |
| 8.6 | Help Center with FAQs covering deals, messaging, verification, payments, security | Support | Medium |
| 8.7 | Platform-wide QA, performance optimisation, accessibility audit, and launch prep | QA & Polish | Critical |

# 4. Sprint Summary

| Sprint | Weeks | Focus | Key Outcome |
| --- | --- | --- | --- |
| S1 | 1–2 | Foundation & Auth | Both roles can sign up and log in |
| S2 | 3–4 | Creator Profile | Fully browseable creator profile live |
| S3 | 5–6 | Discovery & Explore | Brands can find creators by category/filter |
| S4 | 7–8 | Packages & Quick Deal | Brands can purchase or initiate deals |
| S5 | 9–10 | Messaging | Real-time brand-creator chat |
| S6 | 11–12 | Orders & Campaign Tracking | Full order lifecycle operational |
| S7 | 13–14 | Payments, Reviews & Admin | Escrow payments + admin tools live |
| S8 | 15–16 | Ambassador, Pricing & Launch | Go-to-market ready platform |

— End of Document —

ChamCham Influencer Marketplace  |  v1.0  |  Confidential